# K-EL/01 Comprehensive Gap Closure Plan

Original-brief review, generation plan, acceptance gates and residual unknowns

# 1. Purpose and governing principle

This plan maps each requirement in KR-MECH-INT-001 to a concrete file/evidence item, states what has been generated, defines how to generate/check anything still missing, and prevents assumptions from being presented as verified facts. The challenge explicitly says this is conceptual work; it does not require physical prototype, purchases, detailed FEA or manufacturing-ready drawings.

# 2. Required deliverables versus generated evidence

| Requirement | Brief asks | Evidence/generated output | Acceptance / outstanding |
| --- | --- | --- | --- |
| 1. Calculation sheet | Static torque, target factor, output speed and motor speed/ratio. | Calculations.csv + Engineering Workbook.xlsx + report tables. | Formula and units checked against brief; input cells highlighted in workbook. |
| 2. Component selection | One candidate motor + gearbox with official datasheets/product references. | Component_Research.csv + report with official URLs + Supplier_Clarifications.csv. | Shortlist only; request exact configured combination and loaded curve; not frozen until response. |
| 3. CAD files | Elbow concept and simplified arm assembly; CAD may be FreeCAD/SolidWorks/Fusion/equivalent. | STEP + Build_K_EL01_STEP.py + FCMacro. | STEP re-import valid, 21 solids. Native .FCStd deferred: run macro inside FreeCAD; do not claim macro generated it here. |
| 4. Drawing | One assembly drawing or clearly labelled CAD view. | STEP model plus concept drawing PDF/SVG/PNG. | Views and load paths included; concept dimensions only, no manufacturing tolerances. |
| 5. Draft artwork | One isometric whole arm, enlarged elbow/exploded view, labels/load paths, key dimensions, torque/speed, trade-off note. | K_EL01_Concept_Drawing.pdf/.svg/.png. | One A3 landscape page; perform visual check at full resolution before packaging. |
| 6. BOM | Main components, quantities, manufacturer/model if known. | BOM.csv + workbook BOM sheet. | Separates candidate/catalogue, original concept, conditional and TBD elements; no invented stock number for custom part. |
| 7. Short report | ~3–5 pages; assumptions, critical-thinking answers, two risks, rationale. | Kritva_K_EL01_Design_Report.docx/.pdf. | Target 3–5 PDF pages; DOCX rendered and visually inspected before final release. |
| Critical thinking Q1–Q6 | Brief asks brief answers to each. | Report + speaker Q&A. | Answers checked against source framing. |
| Final review | 10-minute presentation then 10-minute technical discussion. | PPTX/PDF + timed speaker notes + technical Q&A. | User must rehearse/deliver; live review itself cannot be performed by deliverable generation. |
| Original-source audit | Preserve original wording/requirements and show trace. | Original brief PDF included; Assignment_Traceability.csv. | Each original requirement maps to evidence/status; source remains unchanged. |

# 3. Remaining technical closure plan (in order)

| Gate | Actions | Evidence / outputs | Entry/exit rule |
| --- | --- | --- | --- |
| Gate 0 — Clarify system mission | Obtain duty cycle, trajectory, accelerations, max speed, dwell/reversals, impact/stop cases, ambient temperature, accuracy/backlash, life, cable force, load orientation and power-loss holding. | Project lead answers; revised requirement spec and signed assumption log. | Before motor/reducer design freeze; currently open because brief omits these inputs. |
| Gate 1 — Supplier configuration | Send exact motor 579165, GP52C ratio 91:1 candidate, encoder 512 CPT, controller 688770 concept to maxon. Ask compatible configured order number, actual torque-speed curve at 4095 rpm, output torque at 45 rpm, loaded efficiency, thermal limits, continuous/intermittent/duty curves, the 180 W versus nominal Tω power arithmetic, maximum input/output loads and regen needs. Do not treat the EC-i 0.321 rpm/mNm gradient as constant; Maxon support describes its iron-winding speed/torque characteristic as nonlinear. | Written vendor response, official datasheet revision, exact order code and performance point saved to Component_Research and Supplier_Clarifications. | Do not release part numbers or claim operational pass before response. |
| Gate 2 — Transmission interface | Select coupling hubs/bore/key, axial retention, permitted misalignment, peak/reversing torque, service factor, torsional stiffness and speed. Confirm KTR hub compatible with 12 mm spindle and gearhead’s actual keyed output. | Vendor-confirmed coupling assembly and interface sketch. | Current size 19/98ShA is a candidate family only, not full set of order codes. |
| Gate 3 — CAD native file and assembly | Open STEP in FreeCAD (or accepted CAD), execute K_EL01_Split_Yoke_Concept.FCMacro, save .FCStd. Compare it to STEP; inspect object tree/units/orientation. Add proper constraints/joints only if supported by selected CAD package. | Native file saved from CAD; screenshot of assembly tree and isometric; export refreshed STEP. | FreeCAD unavailable in current authoring environment; user/FreeCAD workstation execution needed. |
| Gate 4 — Engineering detail | Specify shaft material/condition, shoulders, keyway, hub contact, retaining features, bearing fits, axial load/retention, seals, bolt grades/preload, flange bolt pattern, housing wall thickness, cable route, motor mount, tolerances and assembly access. | Released detailed drawings and calculation notes, reviewed by mechanical designer. | Not required for conceptual assignment; required before building hardware. |
| Gate 5 — Calculations | Include link inertia, motor rotor/gearhead inertia reflected through ratio, acceleration/deceleration, gravity across full range, impact/stop events, peak and RMS torque/current, output deflection, shaft combined stress with notch/ fatigue, key/hub contact, fasteners, carrier stiffness, bearing L10/oscillation and thermal equilibrium. | Updated calculation workbook; independent engineering review; explicit pass/fail thresholds derived from requirements. | Current static screens are inadequate for final release. |
| Gate 6 — Digital analysis | Perform CAD interference/motion checks; hand calculations first; FEA for yoke/shaft/flange only if useful, with mesh convergence, boundary-condition rationale and load cases. Use bearing/vendor tools for life and manufacturer reducer sizing tool. | Native model, assumptions, solver/settings, mesh convergence, plots and output tables. | FEA is explicitly not required in assignment; do not manufacture simulation output without running it. |
| Gate 7 — Safety and controls | Define safe state and power-loss hold. If gravity-load hold required, size normally engaged brake (including margin and release logic) or external support. Validate emergency stop, limits, encoder polarity, regenerative bus and controller derating. | Control concept, brake data or explicit excluded operating envelope, interface schematic and risk assessment. | No brake selected; supervised de-energized setup must remain externally supported. |
| Gate 8 — Bench verification (future, not assignment task) | Only after component configuration and detailed design: guarded, restrained test stand, no personnel under load, increment torque/speed; measure output torque/speed, current, temperature, backlash and stop response. | Calibrated test setup, protocol, raw logs, uncertainty statement, comparison against requirement thresholds. | No hardware purchased/manufactured; this gate is a future plan, not reported as performed. |
| Gate 9 — Release decision | Close every requirement and hazard; resolve supplier clarifications; sign drawings/BOM/configuration; archive revision, source, test evidence and review approval. | Design review record and controlled release package. | Current package stays “assignment concept only”. |

# 4. Suggested 5-day execution plan (aligned to brief duration)

| Day | Activities | End-of-day evidence / acceptance |
| --- | --- | --- |
| Day 1 — Requirements & sizing | Extract brief; establish source/assumption log; torque, power and speed math; identify missing duty/accuracy inputs. | Reviewed calculation sheet and clarification list; all units and assumptions traceable. |
| Day 2 — Drive shortlist | Compare motor/reducer candidates, official references, ratio, current/power/efficiency sensitivity and controller/encoder options. | Candidate stack and supplier questions; do not call it selected until configured point is validated. |
| Day 3 — Architecture & CAD | Create support-bearing load path, actuator envelope, simplified arm/wrist, assembly view, link lengths and assembly access review. | Valid STEP, editable builder source/macro, key dimensions and drawing export. |
| Day 4 — Risk, report and artwork | BOM, six Q answers, two major risks, one-page artwork, traceability, design/verification register. | 3–5 page report, drawing PDF/SVG/PNG, risk and gap registers. |
| Day 5 — QA & presentation | Peer review calculations/files, render every PDF/DOCX page and slides, archive checksums, rehearse 10-minute talk and Q&A. | Integrity-checked release package and clear residual-risk statement. |

# 5. Required acceptance checklists

Calculation acceptance: inputs match brief; torque terms independently recomputed; units are visible on every equation; target factor labelled assumption; speed ratio and output power reconcile; sensitivity rows recalculate from formulas.

Component acceptance: official part links reachable; revision/date captured; exact order codes and accessories verified; torque-speed-thermal point confirmed; no rated maximum or maximum efficiency represented as guaranteed operating point.

CAD acceptance: file opens without warnings; global unit system stated; part coordinates and assembly placement documented; model geometry valid; no overlap/interference assumed merely from STEP validity; native editable source opened in target CAD and re-export round-trip compared.

Drawing acceptance: whole-arm isometric and enlarged elbow/exploded view; labels distinguish candidate vendor envelopes from original parts; load-path arrows; COM radii and link lengths; torque and speed callout; at least one trade-off/open issue; text readable at 100%.

Report acceptance: 3–5 pages; assumptions and limitations; concise BOM rationale; two risks with mitigations; all Q1–Q6 answered; source URLs; no broken placeholders; consistent spindle/coupling architecture.

Presentation acceptance: 10-minute timed presentation, covering torque math, sizing, component evidence, load path, drawing/CAD, trade-offs and next validation; 10-minute discussion question prep; explicitly acknowledge unknowns.

Package acceptance: generated source/editable file, PDF preview, named versions, index/hash, archive integrity; no intermediate QA image folders in final zip unless explicitly useful.

# 6. Current status and residual open items

At the time of this plan, the concept calculations, one-page artwork, candidate component references, STEP model, source CAD builder/macro, report, BOM and registers can be generated and checked. A native FreeCAD .FCStd file, supplier-confirmed drive combination, real thermal/motion proof, manufacturing detail, controlled safety design and physical-test results cannot responsibly be asserted from the provided assignment input. They have explicit routes and acceptance evidence above.