# K-EL/01 Simulation & Verification Plan

Proposed validation protocol — no analyses or physical tests are represented as completed

# 1. How to use this plan

The original challenge explicitly does not require detailed FEA, manufacturing drawings, component purchases or a physical prototype. The plan below is a staged future verification route. Execute only after required mission inputs and supplier configuration are available; retain raw evidence and record failures, not just successful plots.

| ID | Verification | Scope | Owner | Evidence | Acceptance logic |
| --- | --- | --- | --- | --- | --- |
| V-01 | Requirements review | Duty profile, speed range, accelerations, accuracy/backlash, impacts, temperatures, life, power-loss hold. | Project lead and engineering | Signed requirement/assumption register | All key unknowns answered or formally bounded before design freeze. |
| V-02 | Static torque audit | Horizontal-arm torque and all load directions/ranges; confirm mass/COM includes links/attachments. | Mechanical engineer | Calculation workbook and independent check | Numerical results reconcile; input sources and SI units explicit. |
| V-03 | Drive operating point | Motor torque-speed curve at actual voltage; gear ratio/input speed; loaded efficiency; continuous/intermittent output torque. | Supplier + controls engineer | Configured part-number sheet and curves | Output 45 RPM and target torque achieved simultaneously at defined duty. |
| V-04 | Duty/thermal model | Trajectory and reflected inertia; peak/RMS torque; winding and gearhead heating; temperature rise and derating. | Controls/mechanical engineer | Torque profile, loss model, thermal assumptions | Predicted temperatures below manufacturer limits with defined margin. |
| V-05 | Coupling interface | Hub bore/keyway, shaft diameters, torque reversal, speed, offset/angular misalignment, torsional stiffness. | Mechanical engineer + KTR | Selected hub/spider codes and interface drawing | All torque, speed and misalignment limits satisfied including service factor. |
| V-06 | Spindle strength | Bending+torsion, keyway notch, fatigue, shoulders, retaining grooves, deflection, stress concentrations. | Mechanical engineer | Detailed shaft CAD/drawing and checked report | Margin per agreed design standard and peak/duty load cases; no reliance on smooth-shaft screen alone. |
| V-07 | Bearing and carrier | Radial/axial reactions, L10 and oscillation factors, static safety, fits, lubrication, housing stiffness, fasteners. | Mechanical engineer | Bearing tool output, fit table, structural calculations | Life/stiffness/fit requirements met; vendor constraints observed. |
| V-08 | CAD interference & motion | Full assembly clearance, coupling envelope, fastener access, cable bend, arm sweep, stops, collision. | CAD designer | Native assembly, screenshots, interference report | No unplanned interference over specified swept envelope; maintainability demonstrated. |
| V-09 | Finite-element analysis (optional) | Yoke, flange/root plate and spindle only where hand calculations indicate value. Include realistic contacts, preload, load paths and mesh sensitivity. | FEA-capable engineer | Solver file, mesh convergence, BC/load rationale, stress/displacement plots | Convergence and sensitivity accepted; FEA does not replace bearing, fatigue, or supplier checks. |
| V-10 | Control/safety review | Encoder resolution/placement, polarity, controller limits, emergency stop, regen, brake and fault response. | Controls/safety engineer | Block diagram, configuration, hazard review | Safe state defined; power-loss holding behavior is explicitly met or operation externally supported. |
| V-11 | Bench torque/speed test | Guarded restrained fixture; measure torque and RPM at several duty points and current. | Test engineer | Calibration records, raw CSV, protocol | Performance reaches requirements at actual configured operating point. |
| V-12 | Thermal/duty test | Run representative movement cycle to steady state; monitor winding proxy, casing, gearhead, controller, current and speed. | Test engineer | Raw time series and uncertainty statement | Temperatures stabilize within ratings and current limits for stated duty. |
| V-13 | Backlash/deflection | Apply bidirectional load steps; measure output angle/hub displacement and elastic deflection. | Test engineer | Indicator/encoder logs and test report | Measured reversal error and stiffness meet the explicit position-error budget. |
| V-14 | Final review / release | Reconcile deviations, actions, BOM/order codes, drawings, software config and test results. | Design owner + reviewer | Signed design review record | All requirements passed/waived with accountable owner; no open critical hazard. |

# 2. Minimal later bench setup

Rigid guarded base and restrained arm/fixture; no person under or in plane of suspended arm/payload.

Calibrated torque transducer or lever/force arrangement with known uncertainty, RPM measurement, current/voltage logging and temperature sensors.

E-stop, current limits, mechanical travel stops, cable restraint and safe power-disconnect/regeneration management.

Defined test matrix: unloaded run, low-load direction checks, several static torque points, 45-RPM loaded point, representative trajectory and reversal/backlash measurement.

Predefine abort limits for current, vibration, abnormal noise, temperature, unexpected movement and fixture displacement.

# 3. Current evidence versus planned evidence

| Available now | Not yet available / must not be claimed |
| --- | --- |
| Static calculation from brief inputs; explicit sensitivity analysis; component reference list; valid STEP geometry check; conceptual load/reaction/stress arithmetic. | Supplier-confirmed loaded point, physical torque/speed measurements, thermal steady-state data, measured backlash, detailed FEA, bearing life validation, shaft fatigue assessment, safety certification. |
| Concept architecture and artwork; BOM and registers identify TBDs. | Manufacturing tolerance stack, full fastener/interface calculations, verified power-loss hold solution, test data from actual components. |